## STRUCTURE
| CAFE |  | BAR |  | SOUND LAB
VALUE/PROPOSITION
Define what we sell | High-fidelity ambient listening, premium coffee, and curated light bites. |  | Craft cocktails, specialized spirits, and curated evening soundtracks. |  | Sonic experiences: Live Jazz, DJ sets, and immersive audio events.
Experience driven | A creative "third space" outside of home for focus or quiet social connection. |  | Sensory engagement through taste and sound; a space for "appreciation of the arts." |  | Physical and emotional immersion in music; rhythmic and communal energy.
Atmosphere/Vibe | Harmony, creativity, and "quirky" comfort. Relaxed but intentional. |  | Bold and loud; intimate lighting, moody, and sophisticated. |  | High energy, acoustic excellence, and dynamic movement.
Social Interaction | Casual meetings, creative collaboration, or solo "being yourself." |  | Deep conversations, event dates, and small group bonding. |  | Communal appreciation of music; dancing and collective movement.
Emotional state | Inspired, calm, and grounded. |  | Connected, elevated, and intrigued. |  | Euphoric, expressive, and energized.
Clear Statement | CUR-8 is a destination for the appreciation of the arts and senses, specifically the art of sound.
TARGET CUSTOMER
Customer Personas | The Audiophile, The Creative Professional, The Jazz Enthusiast, The Urban Explorer.
Age Range | 25–55 (Focus on Millennials and Gen X who value curated high-fidelity experiences).
Income level | Mid-to-high (Individuals with disposable income for premium F&B and ticketed events).
Lifestyle/Behaviour | Frequenters of galleries, vinyl collectors, remote workers, and late-night socialites.
Why do they come | To escape the mundane; to "just be themselves"; to experience exclusive sound quality.
How do they spend | Daily coffee/workspace (AM), premium cocktails and event covers/tickets (PM).
PRODUCT ARCHITECTURE (ÁNH) | CAFE |  | BAR |  | SOUND LAB | Detailed Menu
Food | Eggdrops Avocado Toased - V Grilled Cheese Sandwich Chicken Caesar Salad Green Salad Croissants |  | Gỏi Cuốn (Pork & Shrimp) Crispy Rolls (Chả Giò ¦ Nem Chua ¦ Ram bắp) Mac & Cheese Deep fried chicken wings Spicy Wonton Mixed Tempura Corn & Mushroom Salad Fries (Wegdes ¦ Crispy) Platter (Bánh Mì ¦ Cheeses ¦ Cold Cuts ¦ Mixed) Tartare (Tuna ¦ Beef) Churros (Classic ¦ Chocolate)
Drink | Americano Cà Phê Cà Phe Sua Da Matcha Latte Earl grey Jasmine Chocolate |  | Old Fashioned Aperol Sprizt Long Island Iced Tea El Diablo Espresso Martini Daiquiri Mojito Absolut Original 400 Conejos Beefeater Hendrick's Havana Club 3YR Cinzano Rosso Jose Cuervo Especial Reposado Altos Plata | Terre Forti, Sangiovese Maison Castel, Pinot Noir Concha Y Toro, Chadonnay Chantecaile, Bordeaux The Stump Jump, Riesling, McLanren Valey Concha Y Toro, Chadonnay The Stump Jump, Riesling, McLaren Valley Vignobles Jonqueres d'Oriola, Gris-Gris Rose Terre Forti Sparkling Telmont Reserve Brut Jagermeister Aperol Saigon Special Heineken Fresh Orange Cranberry Juice Lavie Lavie Sparkling Soda water Coca Sprite Tonic | Old Fashioned Aperol Sprizt Long Island Iced Tea El Diablo Espresso Martini Daiquiri Mojito
Purpose
REVENUE MODEL | F&B | Event/Venue
Direct Revenue
Indirect Revenue: • Private events / bookings • Brand collaborations • High-margin drivers: • Signature drinks • Group orders / bottles • Upselling strategy
Cost Benchmarks Food cost: Beverage cost Rent
UNIT ECONOMICS
• Average bill (day vs night) • Seating capacity • Table turnover rate • Core formula: • Daily Revenue = Seats × Turnover × Avg Bill • Define: • Peak hours vs off-peak strategy
Brand Positioning
Mid-premium (lifestyle-driven)
• Align: • Pricing • Service level • Interior design • Customer expectations
OPERATING MODEL ( BUSH)
Music direction
Vibe
Lighting
Ticket?
Programming - DJ/Jazz/Playlist
Operations Model (Bách+Ánh) | SL | Roles
Team structure
VŨ+KELLY+PA+BUSH
General Manager (kế toán chi) | 1
Inhouse general accountant (kế toán thu) / Cashier | 1
Supervisor | 1
Bar leader | 1
Bar staff | 3
Server leader | 1
Server | 2
Kitchen staff
Shift design
Day shift
Night shift
Marketing Engine (Vu+Phuong Anh)
Social first brand
Content pillars: Space Music Drink/food People/vibe
Preopening: Teasing Behind-the-scenes Soft-opening events
EXECUTION BRIDGE | APERO | JAY | Rượu Con Rồng | ALCHEMY | Cellier D'asie | Mega Market
Collected supply list | Apero - Spicy Vodka Sauce Apero - Pesto Sauce Apero - Bolgnese Sauce Duck Terrine | Mushroom Pie Chocolate Chunk Cookies Miso Cookies Croisant plain Palmer | Absolut Original Absolut Elyx Beefeater Hendrick's Havana Club 3YR Bumbu XO Altos Plata Jameson Irish Deacon Aberlour 12 YR Creme de Cassis Amarretto Liqueur Kahlua | Jose Cuervo Especial Reposado 400 Conejos Jagermeister Aperol Cointreau Cinzano Rosso Cinzano Extra Dry Telmont Reserve Brut | Maison Castel, Pinot Noir Chantecaile, Bordeaux The Stump Jump, Riesling, McLanren Valey Concha Y Toro, Chadonnay Terr Forti, Sangiovese Vignobles Jonqueres d'Oriola, Gris-Gris Rose Terre Forti Sparkling | Soda water Coca Sprite Tonic Ginger Ale Sugar - White Acid Citric Lime no seed Mint leave Fresh Ginger Fresh Orange - US Fresh Orange Cranberry Juice Lavie Lavie Sparkling Saigon Special Heineken Cacao powder Meiji Blue Milk Anchor UHT Whipping Cream 1L
Hiring Profile (HR) - Ánh | yêu cầu về profile
MARKETING (KISU/VU+PA)
Persona
Posting schedule (story+post)
Printing
POSM
Concept Statement
Target customer personas
Day+night strategy
Brand positioning

## Sheet3
Category | Customer Profile | BAR | SOUND LAB
Customer Personas | The Audiophile, The Creative Professional, The Jazz Enthusiast, The Urban Explorer. | Craft cocktails, specialized spirits, and curated evening soundtracks. | Sonic experiences: Live Jazz, DJ sets, and immersive audio events.
Age Range | 25–55 (Focus on Millennials and Gen X who value curated high-fidelity experiences). | Sensory engagement through taste and sound; a space for "appreciation of the arts." | Physical and emotional immersion in music; rhythmic and communal energy.
Income level | Mid-to-high (Individuals with disposable income for premium F&B and ticketed events). | Bold and loud; intimate lighting, moody, and sophisticated. | High energy, acoustic excellence, and dynamic movement.
Lifestyle/Behaviour | Frequenters of galleries, vinyl collectors, remote workers, and late-night socialites. | Deep conversations, event dates, and small group bonding. | Communal appreciation of music; dancing and collective movement.
Why do they come | To escape the mundane; to "just be themselves"; to experience exclusive sound quality. | Connected, elevated, and intrigued. | Euphoric, expressive, and energized.
How do they spend | Daily coffee/workspace (AM), premium cocktails and event covers/tickets (PM).

## TIMELINE
Ngày bắt đầu điều chỉnh BVKT: 16/04/2026 |  |  | Nghỉ lễ hoàn toàn: 26/04/2026 – 01/05/2026
PHASE | CUR8 TEAM TASKS | DATE | DURATION | CONSTRUCTION
Giai đoạn chuẩn bị 16/04/2026 - 22/04/2026 | - Họp chốt BG đợt 1 nếu cần ngay T7 hoặc CN - hoặc chốt online (Kelly + Team) - Cùng thầu xử lý vụ xin phép thi công, xin đặt giàn giáo làm mặt tiền, liên hệ với phường (Phượng) - Cầm bản vẽ hiện có -> nói bên tư vấn PCCC tư vấn xem có gì cần lưu ý để bố trí thêm -> xin giấy phép (Phượng) -Tổng hợp danh sách POSM (menu, takeaway, coaster, souvernir, đồng phục...) và biển hiệu (decal, signage, neon...), kèm chi phí dự kiến (Phương Anh) -Hoàn thiện Brand Guideline -Chốt nguồn nhập đĩa than (Bush) | 16/04 – 18/04/2026 | 3 ngày | Điều chỉnh bản vẽ kỹ thuật (tầng trệt + tầng 1) → báo giá đợt 1 → chốt báo giá → ký hợp đồng
|  | T2,20/04/2026 – 22/04/2026 | 3 ngày | Đập phá, tháo dỡ theo bản vẽ
Giai đoạn thi công: xây tô, hoàn thiện + nội thất 20/4/2026 - 07/06/206 | -Lên marketing plan: 1)Bắt đầu social media 2)Brand pillars 3) Programming dự kiến (Phương Anh + Vũ + Bush) -Tease social media (Vũ + PA + Bush) -Báo giá chi tiết chi phí cho artist -Test món cocktail (Ánh) -Chốt phương án takeaway packaging + thiết kế tem/bao bì(Ánh + PA) -Chốt shopping list dụng cụ ăn uống (Vũ+Ánh) -Hoàn thiện thiết kế menu + lên mẫu (PA + Ánh) -Lên sales kit bán event (PA + Kelly) | T2,20/04 – 25/04/2026 | 6 ngày | Trình và chốt vật liệu (bao gồm comment), triển khai trước khi nghỉ lễ 26/04
|  | 23/04/2026 | 1 ngày | Lắp đặt giàn giáo để thi công mặt tiền
|  | 23/04 – 14/05/2026 | 2.5 tuần + 6 ngày lễ | Thi công khung sắt mặt tiền và hoàn thiện sơn hiệu ứng mặt tiền
|  | 23/04 – 09/05/2026 | 1.5 tuần + 6 ngày lễ | Thi công điện nước âm
|  | 23/04 – 09/05/2026 | 1.5 tuần + 6 ngày lễ | Thi công điện lạnh
|  | 23/04 – 09/05/2026 | 1.5 tuần + 6 ngày lễ | Thi công chống thấm
|  | 26/04 – 01/05/2026 | NGHỈ LỄ
|  | 27/04 – 29/04/2026 | 3 ngày (chốt online trong lễ) | Hoàn thành BVKT đợt 2 (tầng 2 & tầng 3) + báo giá đợt 2 + chốt bản vẽ đồ gỗ
| -Đăng ký tài khoản ngân hàng chi nhánh (Phượng) -Setup POS + Payoo (Ánh) -On board nhân sự, bàn giao operation cho Uyên GM (Ánh) -Mua đồ dùng - máy POS, điện thoại quán, dụng cụ ăn uống, dụng cụ bếp (Ánh/Uyên + Kelly + PA) -Sản xuất đồng phục (PA) -Chuẩn bị hợp đồng cho artists thường xuyên (Vũ) - | 04/05 - 10/05/2026 | 1 tuần | Review bản vẽ shopdrawing đồ gỗ, chốt mẫu vật liệu
|  | 11/05 – 24/05/2026 | 2 tuần | sản xuất nội thất (đồ gỗ)
|  | 11/05 – 17/05/2026 | 1 tuần | Thi công ốp lát (sau khi điện lạnh + điện nước âm + chống thấm hoàn tất)
|  | 18/05/2026 | 1 ngày | Nhận toàn bộ thiết bị + Cẩu thiết bị lên tầng bếp và office
|  | 18/05 - 24/05/2026 | 1 tuần | Nhận các thiết bị ở các tầng khác
|  | 25/05/2026 | 1 ngày | Lắp đặt thiết bị inox của bếp
|  | 18/05 – 28/05/2026 | 1.5 tuần | Thi công mái và bao che khu bếp
|  | 18/05 – 28/05/2026 | 1.5 tuần | Thi công thạch cao, sơn nước toàn nhà
|  | 25/05 - 7/6/2025 | 2 tuần | Thi công đồ gỗ
Giai đoạn hoàn thành 08/06/2026 - 18/06/2026 | - Venue photoshoot (nhờ Eigh-T) -Sản xuất menu, POSM | 08/06 - 13/6/2026 | 6 ngày | Lắp đặt thiết bị vệ sinh, đèn + Logo + Signage
|  | 14/6 - 18/6/2026 | 5 ngày | Defect + Vệ sinh + Bàn giao